## Sheet1
Date | # Hours | Description of work | Total | 25.5
12.01.2025 | 1 | I spent time brainstorming the main idea for my project by reviewing my past work to analyze its strengths and identify areas for improvement. I focused on finding a completely new scope of work that could add unique value and elevate the project's impact. | Left | 94.5
17.01.2025 | 2 | I wrote a project proposal and conducted research to establish the domain, define the problem. Created project contract.
20.01.2025 | 3 | Explore existing literature to identify knowledge gaps. This included developing hypotheses, outlining the research design, methodology, technologies, and expected results, emphasizing how the findings could address practical challenges and contribute to the field. Created Repo on GitHub.
21.01.2025 | 2 | Reading different articles, watching YouTube videos about regarding AI and chatbot implementation.
23.01.2025 | 1.5 | I wrote a project proposal (section project planning and timeline). Creating Gantt Chart.
03.02.2025 | 2 | I started by creating my Spring Boot project and setting up the pom.xml file, ensuring the correct dependencies were included for the initial setup. I added a welcome.html page as the main landing page and configured a HomeController to serve it properly. Along the way, I encountered SQL database connection issues, which I resolved by correctly configuring application.properties with the necessary MySQL settingt. I implemented SecurityConfig.java, allowing public access to specific pages so that I wouldn’t need to log in every time. Additionally, I had issues displaying images, which I resolved by placing them in the static/images/ directory and updating the image paths in the HTML.
04.02.2025 | 1 | I worked on integrating my IntelliJ IDEA project with an existing GitHub repository through the desctop version, ensuring proper Git initialization, remote repository linking, and successfully committing and pushing my code.
05.02.2025 | 1.5 | I worked on refining the user registration process for the login page in my application. After users click "Register" on the login page, they are redirected to a user type selection page. I configured Spring Security to allow access to the /select-user-type endpoint, ensuring that users can view this page without needing to authenticate. Additionally, I updated the SecurityConfig to manage redirections correctly and resolved an HTTP 403 (Forbidden) error by adjusting the necessary permissions. I also verified that the "Go Back" button on the selection page accurately redirects users back to the login page.
07.02.2025 | 2.5 | I worked on setting up the user registration flow for the NativeSpark project. Currently, I am implementing a multi-step registration process where users first select their type: Business, Indigenous Entrepreneur, or Basic User. For business users, I have designed a two-step process. In Step 1, users provide their email, password, and user type, which are stored in the users table. In Step 2, users enter their business details and upload a logo, which is saved in the business_users table. I have set up the necessary entities (User and BusinessUser), as well as repositories, services, and controllers to manage data persistence and form submission. Additionally, I created Thymeleaf templates for the registration pages. I also spent time debugging issues related to database mapping. Despite these efforts, saving BusinessUser data in the database is still not functioning correctly, and I will need to continue troubleshooting this issue in the next session. I also plan to implement a similar process for the other two user types.
09.02.2025 | 3 | I focused on debugging the issue where user data wasn't saved in the database after Step 2 of registration. Initially, there were errors with the @JoinColumn reference in the BusinessUser entity. After fixing this, I encountered another problem: uploaded logo files were not being saved correctly, leading to an error. I updated the BusinessUserService to ensure the upload directory exists before saving files. The application was trying to save files in a non-existent directory within the Tomcat temporary workspace. I modified the code to create the directory if it didn't exist and changed the file-saving logic to use `Files.copy()`, ensuring proper storage of uploaded files. I implemented the Entrepreneur User Registration process, following the same structure as the Business User Registration. Similar to the Business Registration, the entrepreneur registration consists of two steps. In Step 1, the user enters their email and password, which are stored in the users table with the user_type set to "ENTREPRENEUR." In Step 2, the user provides personal details, including their first name, last name, a brief description about themselves, indigenous identity, and a profile photo. This information is saved in the entrepreneur_users table and is linked to the corresponding user. Writing logs and progress report 1.
11.02.2025 | 2.5 | I implemented the Basic User Registration process, following the same structure as the Entrepreneur User Registration. Similar to the Entrepreneur Registration, the basic registration consists of two steps. In Step 1, the user enters their email and password, which are stored in the users table with the user_type set to "BASIC." In Step 2, the user provides personal details, including their first name, last name, a brief description about themselves, and a profile photo. This information is saved in the basic_users table and is linked to the corresponding user. This time without debugging issues. Initially, passwords were stored in plain text, but I needed to implement encryption using a PasswordEncoder. I updated the UserService class to include password encoding before saving user data to the database. However, I encountered an issue because UserService implemented UserDetailsService but did not override the `loadUserByUsername(String username)` method. This omission caused an error during the authentication setup in SecurityConfig.java. To resolve this, I implemented the missing `loadUserByUsername` method in UserService, ensuring that it retrieves user data from the database and returns a UserDetails object. This change enabled authentication to function properly with Spring Security. Additionally, I updated the authentication manager in SecurityConfig to utilize UserService for user authentication and to encode passwords before validation. Some modifications in htmls files.
12.02.2025 | 1 | Today, I added a confirmation message for successful registration. However, I encountered an issue where the data from Step 2 of the business registration process was not being saved to the database. After debugging, I discovered that the problem was caused by the `event.preventDefault();` call in the form submission, which was preventing the form from sending data to the backend. To resolve this issue, I removed the `onsubmit` event. Once I verified that the business registration flow was working correctly, I implemented the same functionality for the Entrepreneur and Basic User registration processes to ensure consistency across all user types. New page subscription, need to connect it to all users.
13.02.2025 | 2.5 | Styling home page. I was trying to implement subscription as step 3 of registration, but half way throug decided to leave for future account settings.