## Sheet1
Date | # Hours | Description of work | Total | 16.5
12.01.2025 | 1 | I spent time brainstorming the main idea for my project by reviewing my past work to analyze its strengths and identify areas for improvement. I focused on finding a completely new scope of work that could add unique value and elevate the project's impact. | Left | 103.5
17.01.2025 | 2 | I wrote a project proposal and conducted research to establish the domain, define the problem. Created project contract.
20.01.2025 | 3 | Explore existing literature to identify knowledge gaps. This included developing hypotheses, outlining the research design, methodology, technologies, and expected results, emphasizing how the findings could address practical challenges and contribute to the field. Created Repo on GitHub.
21.01.2025 | 2 | Reading different articles, watching YouTube videos about regarding AI and chatbot implementation.
23.01.2025 | 1.5 | I wrote a project proposal (section project planning and timeline). Creating Gantt Chart.
03.02.2025 | 2 | I started by creating my Spring Boot project and setting up the pom.xml file, ensuring the correct dependencies were included for the initial setup. I added a welcome.html page as the main landing page and configured a HomeController to serve it properly. Along the way, I encountered SQL database connection issues, which I resolved by correctly configuring application.properties with the necessary MySQL settingt. I implemented SecurityConfig.java, allowing public access to specific pages so that I wouldn’t need to log in every time. Additionally, I had issues displaying images, which I resolved by placing them in the static/images/ directory and updating the image paths in the HTML.
04.02.2025 | 1 | I worked on integrating my IntelliJ IDEA project with an existing GitHub repository through the desctop version, ensuring proper Git initialization, remote repository linking, and successfully committing and pushing my code.
05.02.2025 | 1.5 | I worked on refining the user registration process for the login page in my application. After users click "Register" on the login page, they are redirected to a user type selection page. I configured Spring Security to allow access to the /select-user-type endpoint, ensuring that users can view this page without needing to authenticate. Additionally, I updated the SecurityConfig to manage redirections correctly and resolved an HTTP 403 (Forbidden) error by adjusting the necessary permissions. I also verified that the "Go Back" button on the selection page accurately redirects users back to the login page.
07.02.2025 | 2.5 | I worked on setting up the user registration flow for the NativeSpark project. Currently, I am implementing a multi-step registration process where users first select their type: Business, Indigenous Entrepreneur, or Basic User. For business users, I have designed a two-step process. In Step 1, users provide their email, password, and user type, which are stored in the users table. In Step 2, users enter their business details and upload a logo, which is saved in the business_users table. I have set up the necessary entities (User and BusinessUser), as well as repositories, services, and controllers to manage data persistence and form submission. Additionally, I created Thymeleaf templates for the registration pages. I also spent time debugging issues related to database mapping. Despite these efforts, saving BusinessUser data in the database is still not functioning correctly, and I will need to continue troubleshooting this issue in the next session. I also plan to implement a similar process for the other two user types.