## Sheet1
Date | # Hours | Description of work |  | Total | 56.37
12.01.2025 | 1 | I spent time brainstorming the main idea for my project by reviewing my past work to analyze its strengths and identify areas for improvement. I focused on finding a completely new scope of work that could add unique value and elevate the project's impact. |  | Left | 63.63
17.01.2025 | 2 | I wrote a project proposal and conducted research to establish the domain, define the problem. Created project contract.
20.01.2025 | 3 | Explore existing literature to identify knowledge gaps. This included developing hypotheses, outlining the research design, methodology, technologies, and expected results, emphasizing how the findings could address practical challenges and contribute to the field. Created Repo on GitHub.
21.01.2025 | 2 | Reading different articles, watching YouTube videos about regarding AI and chatbot implementation.
23.01.2025 | 1.5 | I wrote a project proposal (section project planning and timeline). Creating Gantt Chart.
03.02.2025 | 2 | I started by creating my Spring Boot project and setting up the pom.xml file, ensuring the correct dependencies were included for the initial setup. I added a welcome.html page as the main landing page and configured a HomeController to serve it properly. Along the way, I encountered SQL database connection issues, which I resolved by correctly configuring application.properties with the necessary MySQL settingt. I implemented SecurityConfig.java, allowing public access to specific pages so that I wouldn’t need to log in every time. Additionally, I had issues displaying images, which I resolved by placing them in the static/images/ directory and updating the image paths in the HTML.
04.02.2025 | 1 | I worked on integrating my IntelliJ IDEA project with an existing GitHub repository through the desctop version, ensuring proper Git initialization, remote repository linking, and successfully committing and pushing my code.
05.02.2025 | 1.5 | I worked on refining the user registration process for the login page in my application. After users click "Register" on the login page, they are redirected to a user type selection page. I configured Spring Security to allow access to the /select-user-type endpoint, ensuring that users can view this page without needing to authenticate. Additionally, I updated the SecurityConfig to manage redirections correctly and resolved an HTTP 403 (Forbidden) error by adjusting the necessary permissions. I also verified that the "Go Back" button on the selection page accurately redirects users back to the login page.
07.02.2025 | 2.5 | I worked on setting up the user registration flow for the NativeSpark project. Currently, I am implementing a multi-step registration process where users first select their type: Business, Indigenous Entrepreneur, or Basic User. For business users, I have designed a two-step process. In Step 1, users provide their email, password, and user type, which are stored in the users table. In Step 2, users enter their business details and upload a logo, which is saved in the business_users table. I have set up the necessary entities (User and BusinessUser), as well as repositories, services, and controllers to manage data persistence and form submission. Additionally, I created Thymeleaf templates for the registration pages. I also spent time debugging issues related to database mapping. Despite these efforts, saving BusinessUser data in the database is still not functioning correctly, and I will need to continue troubleshooting this issue in the next session. I also plan to implement a similar process for the other two user types.
09.02.2025 | 3 | I focused on debugging the issue where user data wasn't saved in the database after Step 2 of registration. Initially, there were errors with the @JoinColumn reference in the BusinessUser entity. After fixing this, I encountered another problem: uploaded logo files were not being saved correctly, leading to an error. I updated the BusinessUserService to ensure the upload directory exists before saving files. The application was trying to save files in a non-existent directory within the Tomcat temporary workspace. I modified the code to create the directory if it didn't exist and changed the file-saving logic to use `Files.copy()`, ensuring proper storage of uploaded files. I implemented the Entrepreneur User Registration process, following the same structure as the Business User Registration. Similar to the Business Registration, the entrepreneur registration consists of two steps. In Step 1, the user enters their email and password, which are stored in the users table with the user_type set to "ENTREPRENEUR." In Step 2, the user provides personal details, including their first name, last name, a brief description about themselves, indigenous identity, and a profile photo. This information is saved in the entrepreneur_users table and is linked to the corresponding user. Writing logs and progress report 1.
11.02.2025 | 2.5 | I implemented the Basic User Registration process, following the same structure as the Entrepreneur User Registration. Similar to the Entrepreneur Registration, the basic registration consists of two steps. In Step 1, the user enters their email and password, which are stored in the users table with the user_type set to "BASIC." In Step 2, the user provides personal details, including their first name, last name, a brief description about themselves, and a profile photo. This information is saved in the basic_users table and is linked to the corresponding user. This time without debugging issues. Initially, passwords were stored in plain text, but I needed to implement encryption using a PasswordEncoder. I updated the UserService class to include password encoding before saving user data to the database. However, I encountered an issue because UserService implemented UserDetailsService but did not override the `loadUserByUsername(String username)` method. This omission caused an error during the authentication setup in SecurityConfig.java. To resolve this, I implemented the missing `loadUserByUsername` method in UserService, ensuring that it retrieves user data from the database and returns a UserDetails object. This change enabled authentication to function properly with Spring Security. Additionally, I updated the authentication manager in SecurityConfig to utilize UserService for user authentication and to encode passwords before validation. Some modifications in htmls files.
12.02.2025 | 1 | Today, I added a confirmation message for successful registration. However, I encountered an issue where the data from Step 2 of the business registration process was not being saved to the database. After debugging, I discovered that the problem was caused by the `event.preventDefault();` call in the form submission, which was preventing the form from sending data to the backend. To resolve this issue, I removed the `onsubmit` event. Once I verified that the business registration flow was working correctly, I implemented the same functionality for the Entrepreneur and Basic User registration processes to ensure consistency across all user types. New page subscription, need to connect it to all users.
13.02.2025 | 2.5 | Styling home page. I was trying to implement subscription as step 3 of registration, but half way throug decided to leave for future account settings.
14.02.2025 | 2 | Setting up the loging for users. Need to start again.
16.02.2025 | 3 | Trial number two to set up login for users, unfortunately broke whatever had before.
23.02.2025 | 3 | I have started from scratch developing the login access to the account for users, the programm logges in via users table. At this trial i also had some issues, my login wasn’t working due to a conflict between the Authentication class from Apache Tomcat and the one from Spring Security. This conflict caused the authentication check to fail, preventing the user session from being recognized. Consequently, after logging in, the system redirected me back to the login page instead of taking me to the account page. To resolve this issue, I removed the incorrect import (org.apache.tomcat.util.net.openssl.ciphers.Authentication), ensured I was using org.springframework.security.core.Authentication, and updated my AccountController to properly verify if a user was authenticated using Spring Security.
23.02.2025 | 2 | Writing Midterm Report, How to Run The Program document, recording Video and etc.
03.03.2025 | 2.75 | After logging into my account, I focused on displaying user-specific details based on different user types: Basic, Business, and Entrepreneur. Initially, I could only see the email and user type, but additional details like names, descriptions, and logos were absent. The issue stemmed from my AccountController, which was retrieving user-specific entities (e.g., BusinessUser, EntrepreneurUser, etc.), but the data was not being correctly passed to the Thymeleaf template. After debugging, I ensured that the correct user details were loaded and properly mapped. As a result, I was able to fix the missing information. However, the logo for business users still wasn't showing because the uploaded images were stored in the uploads directory rather than in the static directory, which prevented Thymeleaf from accessing them directly. I adjusted the image path handling to serve the uploaded images properly, and after that, everything displayed correctly. Additionally, I implemented a logout feature for all users. While users are logged in, they can navigate within the platform, including the "My Account" page, but once they log out, they cannot access the "My Account" page anymore.
04.03.2025 | 2.67 | Today, I worked on implementing the subscription change feature within the user accounts of my web application. When users register, they receive a Free subscription by default. I wanted to give them the option to upgrade or downgrade their plan from their account settings. Initially, I encountered an issue where the subscription wasn’t updating in the database. I resolved this by ensuring the backend correctly retrieved the authenticated user and updated their subscription information in the database. Next, I faced a "bootstrap is not defined" error when trying to display the confirmation modal. This occurred because Bootstrap’s JavaScript file wasn’t loaded properly. I fixed this by adding the correct Bootstrap JS file just before the closing </body> tag. After that, I encountered another problem: the frontend failed with the error "Unexpected token 'S'" when saving the subscription. This happened because the backend was returning a plain text response instead of JSON. To fix this, I made the backend send a JSON response and updated the frontend to properly parse it.
05.03.2025 | 2.67 | Today, I began by separating the controller logic for each user type: Business, Entrepreneur, and Basic. This allowed me to test and manually update the HTML form, ensuring that user data was being correctly updated. Initially, I entered the update paths manually in the HTML form for each user type to verify the data submission process. After confirming that the updates worked for each type individually, I combined all three user types into a single controller. This new setup would handle updates dynamically based on the logged-in user's type. However, I encountered an issue where the "Save" button did not appear when clicking "Edit," and the file input for logos/photos was not enabling for Entrepreneur and Basic users. I resolved this by adjusting the JavaScript to check the user type before enabling the appropriate fields, ensuring that only the relevant inputs were editable for each user type. | 9 | 10 | 11 | 50
06.03.2025 | 1.88 | I was working on enabling file uploads so that Business users could upload a logo, while Entrepreneur and Basic users could upload a profile photo. I also needed to ensure that these updates reflected on the account page. The main issue I encountered was that the file input fields were not activating correctly for different user types, and the uploaded images were not being saved to the database properly. I resolved this by adjusting the JavaScript `toggleEdit()` function to enable the correct input based on user type. Additionally, I updated the form to include both logo and photo inputs, and I modified the backend services and controller to correctly handle file uploads, saving them in the appropriate directories. I worked on implementing a transaction system to log subscription changes when users upgrade or downgrade their plans. Previously, changing a subscription only updated the Subscription table without retaining a record of past changes. To address this, I added a Transactions table to store the subscription type, cost, and timestamp whenever a user updates their plan. One challenge I faced was ensuring that transactions were recorded only for paid plans (Basic and Premium) while treating "Free" as a non-billable change. I resolved this by incorporating conditional logic in the backend to log only the relevant changes. Additionally, I tackled a UI issue where canceled profile edits still displayed modified (but unsaved) data. To fix this, I implemented a Cancel button that refreshes the page to reload the original database values. As a result, both subscription changes and profile edits now function smoothly, ensuring data accuracy and proper tracking. | 9 | 20 | 11 | 13
10.03.2025 | 2.87 | Renamed transations table to orders for future differentiation of transactions for the business and the customers. Also had an error when the table was named order. The error occurs because order is a reserved keyword in SQL. Since order is used for ordering results in queries, using it as a table name causes a syntax error. Today, I established the posting functionality for different user types. While the postings are not yet visible on the front end, I have successfully created the necessary tables in the database: job_postings, project_postings, and products. The controller is set up, allowing business users to manage job and project postings, while entrepreneur users can list products for sale. This functionality is role-specific, ensuring that businesses can add job and project postings, whereas entrepreneurs can add products along with images. I also implemented a toggle switch for business users, allowing them to easily switch between job and project postings while ensuring that the correct data is displayed. Additionally, I added a "Back to Account" button to enhance navigation. Access to "My Postings" has been restricted, so Basic users cannot see this option in the navigation menu. During this process, I encountered security role issues and repository mismatches, which I resolved by refining security configurations and adjusting database mappings. | 9 | 18 | 12 | 10
11.03.2025 | 2.53 | Today, I worked extensively on refining the functionalities for posting jobs, projects, and products in my Spring Boot application. I began by ensuring that business users can create job and project postings, while entrepreneurs can list their products for sale. I organized my Thymeleaf templates to properly display these listings, making sure that the images for product postings appear correctly and are aligned to the left. I encountered some issues during this process, so I improved the image upload logic for products. This ensures that uploaded images are stored correctly and displayed on the "My Postings" page. | 9 | 13 | 11 | 45
12.03.2025 | 2.58 | Today, I worked on implementing the delete functionality for job postings, project postings, and product postings. Initially, I encountered a "405 Method Not Allowed" error when attempting to delete a posting. This issue arose because the delete request was being blocked by CSRF protection in Spring Security. Additionally, using @DeleteMapping directly in the controller did not function properly with Thymeleaf forms, which default to sending POST requests. To resolve this, I modified the Thymeleaf delete buttons to include a hidden input field with _method=DELETE. This change allowed the form to properly send a DELETE request while still adhering to CSRF protection. I also updated the controllers to use @PostMapping for the delete endpoints instead of @DeleteMapping, ensuring that requests were correctly processed. I have implemented the Edit Posting functionality, making updates to both the frontend and backend of my application. On the frontend, I created an HTML page that maintains consistent styling with the job and project editing pages. Additionally, I added an image upload field, allowing users to update their product image while retaining the existing one if no new file is provided. On the backend, I made several important modifications to the ProductPostingController to support the editing feature. I introduced a GET mapping to load the existing product data into the form and a POST mapping to handle updates. The controller retrieves the product by its ID, ensuring that only authenticated entrepreneurs can modify their own postings. I also implemented logic to manage image file updates, so if a new image is uploaded, the old one is replaced; otherwise, the previous image remains unchanged. | 9 | 20 | 11 | 55
13.03.2025 | 2.92 | Today, I refined the home page functionality to ensure different types of users, including non-logged-in visitors, see the appropriate content. I solved an issue where unauthenticated users were wrongly redirected to the login page by adjusting the controller logic to keep the product list accessible to everyone. I also addressed a problem with product images not displaying for non-logged-in users due to incorrect image path references. I fixed this by updating the Thymeleaf syntax to properly serve images from the static resources directory. For entrepreneur users, I implemented a toggle bar to switch between products, job postings, and project postings. The challenge was keeping the clicked button visually active (highlighted in blue). I resolved this by using JavaScript to toggle Bootstrap classes, ensuring only the active button remained highlighted. Moreover, I fixed internal server errors (500) that occurred when entrepreneur users clicked "Home" in the navbar by updating the controllers to ensure the correct data was fetched for different user roles. Lastly, I improved the navbar behavior so that clicking "Home" directs users to the correct page based on their authentication status and role. Entrepreneurs can now see products, jobs, and projects, while basic users can only view products. These changes greatly enhanced the user experience and navigation consistency. I encountered an issue where removing some commented-out code caused the home button in the navbar to malfunction for unauthenticated users, redirecting them to the login page instead of displaying products. This was confusing since the home page should be accessible to everyone. Upon investigation, I found that the commented-out code contained crucial configurations that affected user authentication behavior. To fix the issue, I made sure products were visible to all users, allowing both authenticated and unauthenticated individuals to browse without needing to log in. | 9 | 10 | 12 | 5