## Sheet1
Date | # Hours | Description of work |  | Total | 43.59
12.01.2025 | 1 | I spent time brainstorming the main idea for my project by reviewing my past work to analyze its strengths and identify areas for improvement. I focused on finding a completely new scope of work that could add unique value and elevate the project's impact. |  | Left | 76.41
17.01.2025 | 2 | I wrote a project proposal and conducted research to establish the domain, define the problem. Created project contract.
20.01.2025 | 3 | Explore existing literature to identify knowledge gaps. This included developing hypotheses, outlining the research design, methodology, technologies, and expected results, emphasizing how the findings could address practical challenges and contribute to the field. Created Repo on GitHub.
21.01.2025 | 2 | Reading different articles, watching YouTube videos about regarding AI and chatbot implementation.
23.01.2025 | 1.5 | I wrote a project proposal (section project planning and timeline). Creating Gantt Chart.
03.02.2025 | 2 | I started by creating my Spring Boot project and setting up the pom.xml file, ensuring the correct dependencies were included for the initial setup. I added a welcome.html page as the main landing page and configured a HomeController to serve it properly. Along the way, I encountered SQL database connection issues, which I resolved by correctly configuring application.properties with the necessary MySQL settingt. I implemented SecurityConfig.java, allowing public access to specific pages so that I wouldn’t need to log in every time. Additionally, I had issues displaying images, which I resolved by placing them in the static/images/ directory and updating the image paths in the HTML.
04.02.2025 | 1 | I worked on integrating my IntelliJ IDEA project with an existing GitHub repository through the desctop version, ensuring proper Git initialization, remote repository linking, and successfully committing and pushing my code.
05.02.2025 | 1.5 | I worked on refining the user registration process for the login page in my application. After users click "Register" on the login page, they are redirected to a user type selection page. I configured Spring Security to allow access to the /select-user-type endpoint, ensuring that users can view this page without needing to authenticate. Additionally, I updated the SecurityConfig to manage redirections correctly and resolved an HTTP 403 (Forbidden) error by adjusting the necessary permissions. I also verified that the "Go Back" button on the selection page accurately redirects users back to the login page.
07.02.2025 | 2.5 | I worked on setting up the user registration flow for the NativeSpark project. Currently, I am implementing a multi-step registration process where users first select their type: Business, Indigenous Entrepreneur, or Basic User. For business users, I have designed a two-step process. In Step 1, users provide their email, password, and user type, which are stored in the users table. In Step 2, users enter their business details and upload a logo, which is saved in the business_users table. I have set up the necessary entities (User and BusinessUser), as well as repositories, services, and controllers to manage data persistence and form submission. Additionally, I created Thymeleaf templates for the registration pages. I also spent time debugging issues related to database mapping. Despite these efforts, saving BusinessUser data in the database is still not functioning correctly, and I will need to continue troubleshooting this issue in the next session. I also plan to implement a similar process for the other two user types.
09.02.2025 | 3 | I focused on debugging the issue where user data wasn't saved in the database after Step 2 of registration. Initially, there were errors with the @JoinColumn reference in the BusinessUser entity. After fixing this, I encountered another problem: uploaded logo files were not being saved correctly, leading to an error. I updated the BusinessUserService to ensure the upload directory exists before saving files. The application was trying to save files in a non-existent directory within the Tomcat temporary workspace. I modified the code to create the directory if it didn't exist and changed the file-saving logic to use `Files.copy()`, ensuring proper storage of uploaded files. I implemented the Entrepreneur User Registration process, following the same structure as the Business User Registration. Similar to the Business Registration, the entrepreneur registration consists of two steps. In Step 1, the user enters their email and password, which are stored in the users table with the user_type set to "ENTREPRENEUR." In Step 2, the user provides personal details, including their first name, last name, a brief description about themselves, indigenous identity, and a profile photo. This information is saved in the entrepreneur_users table and is linked to the corresponding user. Writing logs and progress report 1.
11.02.2025 | 2.5 | I implemented the Basic User Registration process, following the same structure as the Entrepreneur User Registration. Similar to the Entrepreneur Registration, the basic registration consists of two steps. In Step 1, the user enters their email and password, which are stored in the users table with the user_type set to "BASIC." In Step 2, the user provides personal details, including their first name, last name, a brief description about themselves, and a profile photo. This information is saved in the basic_users table and is linked to the corresponding user. This time without debugging issues. Initially, passwords were stored in plain text, but I needed to implement encryption using a PasswordEncoder. I updated the UserService class to include password encoding before saving user data to the database. However, I encountered an issue because UserService implemented UserDetailsService but did not override the `loadUserByUsername(String username)` method. This omission caused an error during the authentication setup in SecurityConfig.java. To resolve this, I implemented the missing `loadUserByUsername` method in UserService, ensuring that it retrieves user data from the database and returns a UserDetails object. This change enabled authentication to function properly with Spring Security. Additionally, I updated the authentication manager in SecurityConfig to utilize UserService for user authentication and to encode passwords before validation. Some modifications in htmls files.
12.02.2025 | 1 | Today, I added a confirmation message for successful registration. However, I encountered an issue where the data from Step 2 of the business registration process was not being saved to the database. After debugging, I discovered that the problem was caused by the `event.preventDefault();` call in the form submission, which was preventing the form from sending data to the backend. To resolve this issue, I removed the `onsubmit` event. Once I verified that the business registration flow was working correctly, I implemented the same functionality for the Entrepreneur and Basic User registration processes to ensure consistency across all user types. New page subscription, need to connect it to all users.
13.02.2025 | 2.5 | Styling home page. I was trying to implement subscription as step 3 of registration, but half way throug decided to leave for future account settings.
14.02.2025 | 2 | Setting up the loging for users. Need to start again.
16.02.2025 | 3 | Trial number two to set up login for users, unfortunately broke whatever had before.
23.02.2025 | 3 | I have started from scratch developing the login access to the account for users, the programm logges in via users table. At this trial i also had some issues, my login wasn’t working due to a conflict between the Authentication class from Apache Tomcat and the one from Spring Security. This conflict caused the authentication check to fail, preventing the user session from being recognized. Consequently, after logging in, the system redirected me back to the login page instead of taking me to the account page. To resolve this issue, I removed the incorrect import (org.apache.tomcat.util.net.openssl.ciphers.Authentication), ensured I was using org.springframework.security.core.Authentication, and updated my AccountController to properly verify if a user was authenticated using Spring Security.
23.02.2025 | 2 | Writing Midterm Report, How to Run The Program document, recording Video and etc.
03.03.2025 | 2.75 | After logging into my account, I focused on displaying user-specific details based on different user types: Basic, Business, and Entrepreneur. Initially, I could only see the email and user type, but additional details like names, descriptions, and logos were absent. The issue stemmed from my AccountController, which was retrieving user-specific entities (e.g., BusinessUser, EntrepreneurUser, etc.), but the data was not being correctly passed to the Thymeleaf template. After debugging, I ensured that the correct user details were loaded and properly mapped. As a result, I was able to fix the missing information. However, the logo for business users still wasn't showing because the uploaded images were stored in the uploads directory rather than in the static directory, which prevented Thymeleaf from accessing them directly. I adjusted the image path handling to serve the uploaded images properly, and after that, everything displayed correctly. Additionally, I implemented a logout feature for all users. While users are logged in, they can navigate within the platform, including the "My Account" page, but once they log out, they cannot access the "My Account" page anymore.
04.03.2025 | 2.67 | Today, I worked on implementing the subscription change feature within the user accounts of my web application. When users register, they receive a Free subscription by default. I wanted to give them the option to upgrade or downgrade their plan from their account settings. Initially, I encountered an issue where the subscription wasn’t updating in the database. I resolved this by ensuring the backend correctly retrieved the authenticated user and updated their subscription information in the database. Next, I faced a "bootstrap is not defined" error when trying to display the confirmation modal. This occurred because Bootstrap’s JavaScript file wasn’t loaded properly. I fixed this by adding the correct Bootstrap JS file just before the closing </body> tag. After that, I encountered another problem: the frontend failed with the error "Unexpected token 'S'" when saving the subscription. This happened because the backend was returning a plain text response instead of JSON. To fix this, I made the backend send a JSON response and updated the frontend to properly parse it.
05.03.2025 | 2.67 | Today, I began by separating the controller logic for each user type: Business, Entrepreneur, and Basic. This allowed me to test and manually update the HTML form, ensuring that user data was being correctly updated. Initially, I entered the update paths manually in the HTML form for each user type to verify the data submission process. After confirming that the updates worked for each type individually, I combined all three user types into a single controller. This new setup would handle updates dynamically based on the logged-in user's type. However, I encountered an issue where the "Save" button did not appear when clicking "Edit," and the file input for logos/photos was not enabling for Entrepreneur and Basic users. I resolved this by adjusting the JavaScript to check the user type before enabling the appropriate fields, ensuring that only the relevant inputs were editable for each user type. | 9 | 10 | 11 | 50
06.03.2025 |  | I was working on enabling file uploads so that Business users could upload a logo, while Entrepreneur and Basic users could upload a profile photo. I also needed to ensure that these updates reflected on the account page. The main issue I encountered was that the file input fields were not activating correctly for different user types, and the uploaded images were not being saved to the database properly. I resolved this by adjusting the JavaScript `toggleEdit()` function to enable the correct input based on user type. Additionally, I updated the form to include both logo and photo inputs, and I modified the backend services and controller to correctly handle file uploads, saving them in the appropriate directories. | 9 | 20